## Sheet1
client | deliverable_app | client_primary_stakeholder | engineering | pgm | updated_by | lastest_update | customer_acv | project_budget | actual_cost | percentage_complete | key_milesontes | why?_and_summary | wins_this_week | goals_for_next_week | risks | other_items
Optum ODI | ODI (Optum Data Intelligence) | Justin Beeker, VP Optum Solution Design | Jeff Smith | Jim Lamb | Jim Lamb | 2024-01-26 | 250000 | 150000 | 100000 | 95% | *App Release Wednesday*App Release Tuesday*Client UAT Friday*Close Project Mid Feb | *This branch of Optum collects data from other healthcare systems to allow them to do an audit to help improve processes. This app will allow them to set up a user portal, collect data including long form answers as well as uploading documents to an Optum server. There will also be a chat option to let all parties communicate. As data is entered it will automatically show percentage compete.*An app that allows Optum and their clients to enter data. This will include the ability to upload documents through the app to an Optum server. There will be a client portal as well as an Admin component to allow Optum to set up different clients. | *This week has been spent preparing for phase 2 of the app. Preparing for kickoff as well as assembling timelines and plans to ensure an on time delivery.*There is still one thing we have a call scheduled to discuss with the OHID team next week and that should be the last thing in phase 1.*Prepped phase 2 work and worked on app refresh logout issues. | *Phase 2 requirements are currently being scoped by Optum*Kickoff Phase 2 Dev | None | https://domo-es.domo.com/page/1109934617